## Sheet1
Project | Start Date | End Date | Activiites | Resource Type | Number of Persons | No of Days | Activity Duration in Person Days
Supportive Supervision RI | 2014-11-01 | 2015-12-01 | Form Design | Technical | 1 | 2 | 2
|  |  | Dashboard Application | Technical | 5 | 75 | 375
|  |  |  | Data Analyst | 1 | 20 | 20
Training
|  |  | Support | Implementer | 1 | 300 | 300
|  |  | Infographiics | Designer | 1 | 25 | 25
|  |  |  | Data Analyst | 1 | 20 | 20
RIPAS | 2014-07-01 | 2015-06-01 | Dashboard Application |  |  |  | 0
|  |  | Form Design |  |  |  | 0
|  |  | Support |  |  |  | 0
|  |  | Infographics | Designer | 1 | 10 | 10
|  |  |  | Data Analyst | 1 | 10 | 10
CYSD-USAID | 2014-11-01 | 2017-12-01 | Form Design |  |  |  | 0
|  |  | Monitoring Application- DI Monitoring | Technical | 2 | 25 | 50
|  |  | Monitoring Framework | Development Professional | 1 | 10 | 10
|  |  | Training | Technical | 1 | 10 | 5
|  |  |  | Development Professional | 1 | 10 | 5
Support
|  |  | Factsheet |  | 1 | 8 | 8
|  |  | Online Kowledge Repository | Technical | 2 |  | 50
CYSD-Water Aid | 2014-12-01 | 2015-12-01 | Form Design | Technical |  |  | 10
Monitoring Application- DI Monitoring
Monitoring Framework
Training
Support
MANTHAN | 2014-12-01 | 2015-03-01 | Application Design | Technical | 1 |  | 25
|  |  | Support | Technical | 1 |  | 6
Supportive Supervision-RMNCHA | 2014-12-01 | 2015-06-01 | Form Design |  |  |  | 0
|  |  | Dashboard Application + Content Management | Technical | 5 |  | 250
|  |  | Dashboard Application | Data Analyst | 1 |  | 16
|  |  | Training |  |  |  | 0
|  |  | Support | Technical | 1 |  | 50
|  |  | Infographics | Designer | 1 |  | 5
EVM Assam | 2014-12-01 | 2015-06-01 | Dashboard Application | Technical | 3 |  | 30
|  |  | Factsheets | Data Analyst | 1 |  | 5
BiharInfo | 2014-10-01 | 2015-03-01 | Support |  |  |  | 0
|  |  | Database Updation | Data Analyst | 2 |  | 20
CPMIS | 2014-10-01 | 2015-03-01 | Database Updation | Data Analyst | 2 |  | 10
|  |  | DevInfo Adaptation - Factsheets | Data Analyst | 1 |  | 5
| 2014-12-01 | 2014-12-01 | Factsheets - Database | Data Analyst | 2 |  | 30
Odisha Factsheets | 2014-12-01 | 2014-12-01 | Factsheets - Database | Data Analyst | 1 |  | 5
Eritriea-Database/Adaptation | 2014-01-01 | 2015-05-01 | Training | Development Professional | 1 |  | 10
|  |  | Offline DevInfo Adaptation | Development Professional | 1 |  | 1
|  |  | DevInfo Database | Development Professional | 2 |  | 10
Malaysia Training | 2015-02-01 | 2015-02-01 | Training | Development Professional | 1 |  | 5
Phillipines ePCA | 2015-01-01 | 2015-04-01 | Application Design | Technical | 4 |  | 300
Training
Support
|  |  |  | Data Analyst | Technical
|  |  | Available Person Days | 216 | 1800
|  |  | Required Person Days | 1410 | 3459
|  |  | Gap Person Days | 1194 | 1659
|  |  | Required No of resources | 5.5278 | 7.6806